Project Plan: Integrated Healthcare App (Django & React)

Document Version: 1.0
Date: October 26, 2023
Project Manager: Kashvi

1️⃣ Project Overview / Objective

Primary Objective: To develop a secure, scalable, and user-friendly full-stack Integrated Healthcare Application that bridges the gap between patients and providers, leveraging Django for the backend and React for the frontend.

Key Goals:

- Build a responsive React frontend with modern UI/UX.

- Develop a robust, secure Django REST API backend with MongoDB.

- Implement real-time features (telemedicine, alerts) using WebSockets.

- Integrate AI-powered safety systems for prescription scanning and drug interaction detection.

- Ensure compliance with healthcare regulations (HIPAA, GDPR).

2️⃣ Scope

| In-Scope ✅ | Out-of-Scope ❌ |
| --- | --- |
| Patient & Doctor Portals (Dashboards, Profiles, Medical Records) | Development of native iOS/Android apps (PWA only for mobile). |
| Appointment Scheduling & Management | Hardware integration for medical devices (planned for future). |
| Telemedicine Module with Video Calls (WebRTC) | Advanced AI diagnostics and predictive analytics (future scope). |
| Prescription Management & AI Safety Scanner (OCR) | Full billing and insurance claims processing integration. |
| Medication Tracker with Reminders | Complex multi-tenant architecture for large hospital chains. |
| Emergency Contact & Alert System | Internationalization & multi-language support (future scope). |
| Patient Community Forum/Features | Blockchain implementation for audit trails (future scope). |
| HIPAA/GDPR Compliant Security & Data Handling |  |

3️⃣ Modules / Major Phases

The project will be executed in five sequential phases:

- Phase 1: Foundation & Setup (Sprints 1-2)

- Phase 2: Core Backend & Frontend Development (Sprints 3-6)

- Phase 3: AI & Real-Time Integration (Sprints 7-8)

- Phase 4: Testing, Security & Compliance (Sprints 9-10)

- Phase 5: Deployment & Handover (Sprint 11)

4️⃣ Detailed Task Breakdown

Legend for Owners:

- BE: Backend Developer

- FE: Frontend Developer

- FSI: Full-Stack Integrator

- AI: AI/ML Engineer

- PM: Project Manager

Phase 1: Foundation & Setup (Sprints 1-2)

| Task ID | Task Description | Owner | Notes & Dependencies |
| --- | --- | --- | --- |
| 1.1 | Project Kick-off & Requirement Finalization | PM | Ensure all team members understand the scope and goals. |
| 1.2 | Set up Django Project, DRF, MongoDB, and CORS | BE | Core backend environment setup. |
| 1.3 | Set up React Project, Routing, and State Management Store | FE | Core frontend environment setup. |
| 1.4 | Design System & UI Component Library (Material-UI) | FE | Create a shared storybook for reusable components. |
| 1.5 | Define API Schema & Data Models | BE, FSI | Critical for establishing the contract between FE and BE. |
| 1.6 | DevOps & CI/CD Pipeline Setup (Docker, GitHub Actions) | FSI | Automate testing and builds from the start. |

Phase 2: Core Backend & Frontend Development (Sprints 3-6)

| Task ID | Task Description | Owner | Notes & Dependencies |
| --- | --- | --- | --- |
| Module: Authentication & User Management |  |  |  |
| 2.1 | Implement JWT Authentication API (Login, Register, Refresh) | BE |  |
| 2.2 | Build Login/Registration Pages & Protected Routes | FE | Depends on 2.1. |
| 2.3 | Develop User Profile Management (Patient/Doctor) | BE, FE | BE creates API, FE builds forms. |
| Module: Medical Records & Dashboard |  |  |  |
| 2.4 | Build Medical Records API (CRUD, FHIR structure) | BE |  |
| 2.5 | Implement Patient & Doctor Dashboards | FE | Includes charts and data visualization. |
| 2.6 | Build Medical Records UI (Timeline, Upload, Viewer) | FE | Depends on 2.4. |
| Module: Appointments & Prescriptions |  |  |  |
| 2.7 | Develop Appointment Scheduling API | BE |  |
| 2.8 | Build Appointment Calendar & Management UI | FE | Depends on 2.7. |
| 2.9 | Create Prescription Management API | BE | Basic CRUD before AI safety checks. |

Phase 3: AI & Real-Time Integration (Sprints 7-8)

| Task ID | Task Description | Owner | Notes & Dependencies |
| --- | --- | --- | --- |
| Module: AI Safety Scanner |  |  |  |
| 3.1 | Integrate Tesseract OCR & Develop Medication Parser | AI |  |
| 3.2 | Build Drug Interaction Database & Safety Check Algorithm | AI |  |
| 3.3 | Create Prescription Upload API with OCR & Safety Checks | BE, AI | BE builds API endpoint, AI provides the service. |
| 3.4 | Develop Prescription Scanner UI with Camera Integration | FE | Depends on 3.3. |
| Module: Real-Time Features |  |  |  |
| 3.5 | Implement Django Channels for WebSockets | BE |  |
| 3.6 | Build WebRTC Signaling & Telemedicine Backend | BE |  |
| 3.7 | Develop Video Call Interface (UI & Controls) | FE | Integrates with backend via WebSockets. |
| 3.8 | Implement Real-time Notifications (Reminders, Alerts) | BE, FE | BE emits events, FE displays them. |

Phase 4: Testing, Security & Compliance (Sprints 9-10)

| Task ID | Task Description | Owner | Notes & Dependencies |
| --- | --- | --- | --- |
| 4.1 | Comprehensive Backend Unit & Integration Testing | BE | Aim for >90% code coverage. |
| 4.2 | Comprehensive Frontend Unit & Integration Testing | FE | Test all components and user flows. |
| 4.3 | End-to-End (E2E) Testing of Critical User Journeys | FSI | e.g., Login -> Schedule -> Video Call -> Get Prescription. |
| 4.4 | Security Audit & Penetration Testing | FSI, BE | Focus on HIPAA/GDPR requirements. |
| 4.5 | Performance & Load Testing | FSI | Ensure backend handles 10k+ concurrent connections. |
| 4.6 | PWA Optimization & Lighthouse Score Improvement | FE | Target score of 95+. |

Phase 5: Deployment & Handover (Sprint 11)

| Task ID | Task Description | Owner | Notes & Dependencies |
| --- | --- | --- | --- |
| 5.1 | UAT (User Acceptance Testing) & Bug Fixing | All | With a select group of beta users. |
| 5.2 | Production Deployment on AWS/Azure | FSI | Ensure healthcare-compliant infrastructure. |
| 5.3 | Final Documentation & Code Handover | All | API docs, setup guides, etc. |
| 5.4 | Post-Launch Monitoring & Support Plan | All |  |

5️⃣ Team Roles & Responsibilities

| Role | Primary Responsibilities | Key Deliverables |
| --- | --- | --- |
| Project Manager (PM) | Project planning, scheduling, risk management, communication, and ensuring timely delivery. | Project Plan, Status Reports, Risk Logs. |
| Backend Developer (BE) | Django REST API development, database design (MongoDB), authentication, WebSockets, Celery tasks, and server-side security. | Secure and documented APIs, Database models, WebSocket consumers. |
| Frontend Developer (FE) | React SPA development, state management (Redux), UI/UX implementation (Material-UI), component library, and PWA features. | Responsive and accessible UI, Functional React components, State slices. |
| AI/ML Engineer (AI) | OCR integration (Tesseract), drug interaction algorithm development, image processing, and safety validation logic. | OCR service, Drug interaction API, Safety check algorithms. |
| Full-Stack Integrator (FSI) | DevOps (CI/CD), API connection troubleshooting, E2E testing, performance optimization, and leading the production deployment. | Dockerized app, CI/CD pipeline, Deployment scripts, Integration test suite. |

6️⃣ Timeline & Milestones

- Sprint Duration: 2 Weeks

- Total Sprints: 11

| Milestone | Sprint | Description | Deliverable |
| --- | --- | --- | --- |
| Kick-off & Foundation | 2 | Completion of Phase 1. Environments ready. | Working dev environments for FE & BE. |
| MVP Core | 6 | Completion of Phase 2. Users can log in, view records, and manage appointments. | Deployed MVP with Auth, Dashboard, and Records. |
| Alpha Release | 8 | Completion of Phase 3. All core features integrated, including AI Scanner and Telemedicine. | Fully functional alpha version for internal testing. |
| Beta Release | 10 | Completion of Phase 4. Application tested, secure, and performance-optimized. | Beta version ready for UAT with external users. |
| Production Launch | 11 | Application successfully deployed to production. | v1.0 Live. |

7️⃣ Progress Tracking Method

- Tool: Jira / Azure DevOps Board.

- Methodology: Scrum with 2-week Sprints.

- Ceremonies:

  - Daily Stand-ups: 15-minute sync for blockers.

  - Sprint Planning: At the start of each sprint.

  - Sprint Review & Demo: At the end of each sprint to showcase working features.

  - Retrospective: After each sprint to improve processes.

- Metrics:

  - Burndown Charts

  - Velocity Tracking

  - Cumulative Flow Diagram

8️⃣ Risk & Issue Management Plan

| Risk ID | Risk Description | Probability | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- |
| R01 | Scope Creep | Medium | High | Strict change control process. All changes require PM approval. | PM |
| R02 | Integration Issues between FE/BE | High | Medium | Early API contract definition. FSI responsible for mediation. | FSI |
| R03 | AI/ML Safety Check Inaccuracy | Medium | High | Rigorous testing with a large dataset of prescriptions. Have a manual review fallback. | AI |
| R04 | Data Security & HIPAA Compliance Breach | High | Critical | Early and frequent security audits. Use encryption (at rest & transit). Train team on compliance. | BE, FSI |
| R05 | Performance Bottlenecks (Real-time features) | Medium | Medium | Early load testing and performance profiling. Use of Redis for caching. | FSI, BE |
| R06 | Team Member Unavailability | Low | High | Cross-training on critical modules. Maintain up-to-date documentation. | PM |

9️⃣ Documentation & Deliverables

| Document | Description | Owner |
| --- | --- | --- |
| Project Charter & Plan | This document. | PM |
| Technical Design Document (TDD) | Detailed API specs, database schema, system architecture. | BE, FSI |
| UI/UX Wireframes & Prototypes | Mockups and design system documentation. | FE |
| Source Code | Well-documented code in the repository. | All |
| API Documentation | Interactive API docs (e.g., using Swagger/OpenAPI). | BE |
| Test Plan & Reports | Unit, integration, and E2E test suites and results. | All |
| User Manuals & Deployment Guides | Instructions for end-users and DevOps. | FSI |
| Final Project Report & Lessons Learned | Summary of achievements and retrospectives. | PM, All |